Research Proposal

In this section you must present your proposal, developing the following aspects: a) Theoretical-conceptual and state-of-the-art developments that underpin the proposal, b) Objectives and hypotheses or research questions, c) Methodology, d) Work Plan or Gantt chart and e) Scientific or technological novelty. Remember that: -You must strictly comply with what is established in the Guidelines of the 2023 Postdoctoral Fondecyt Competition. -All text, paragraphs or textual phrases from a bibliographic reference, whether by other authors or their own, must be duly identified in the text and in the list of references. This file must contain a maximum of 10 pages (use letter size format, Verdana font size 10 or similar).

Is the proposal part of an ongoing proposal of the sponsoring researcher? Check the appropriate alternative:

YES         NO

Keep in mind that, if the proposal is inserted in a proposal in execution of the sponsoring researcher, it must include different or complementary objectives to those already financed in that proposal and declare it in this file (point 6.2. of the guidelines).

1. Fundaments and state-of-the-art

Modern medicine have been challenged by the grown and development of computers. One of the most important goals of the health industry in these days is the personalization of the diagnosis. The majority of the healthcare companies have been targeting the concept of digital twin in their agenda, and for that they mean the feasibility of extract all the important data from one subject, in order to create a model which can be treat as a new patient, opening the possibilities for a full status monitoring and, which is more attractive, the testing of solutions remotely. The word model here is the key factor, since all the complexity of this idea depends on it.

In blood flows, the personalization of spatially distributed (i.e., 3D) models is a key step in performing predictive patient-specific simulations. Such a step relies on the formulation and numerical solution of Inverse Problems using medical images for measuring both anatomy and function of the vasculature. However, since full-scale hemodynamics simulations are not feasible by the large amount of degrees of freedom, reduced-order modelling techniques have become a feasible alternative for realistic modelling of the blood flow.

In that line, lumped parameter models can efficiently deliver realistic boundary conditions, accounting for the effects of the omitted parts of the vascular system at the cost of coupling the main model, based typically on Navier-Stokes equations (NS), with a 0D compartment. The most common alternative here is the so-called three element Windkessel model, which coupled the flow rate and the average pressure introducing some parameters related to the resistance of the flow through that boundary and its ability of inject blood to the system. In this context, the personalization typically relies on estimating those 0D model parameters at each outlet boundary of the 3D model from velocity (and eventually pressure) data. This inverse problem is usually solved using variational or sequential methods. [cites]

The gold standard for distributed blood flow velocity measurements in the clinical context is Phase-Contrast Magnetic Resonance Imaging (PC-MRI) [cites]. However, PC-MRI presents important artifacts, noise and velocity aliasing being the most important ones. When personalizing the models with such data, not taking these artifacts into account can lead to to important inaccuracies in the blood flow model personalization. Time-resolved 3D flow magnetic resonance imaging, also referred to as 4D flow MRI, has shown in the last years increasing potential in assessing cardiovascular diseases since it offers full coverage of the region of interest [cites] an multiple options for visualization and quantification [cites], allowing the computation of several hemodynamic parameters, which can be used as new biomarkers [cites]. However, high-quality 4D flow in subjects involves long time scans (>20 minutes) even with coarse spatio-temporal resolutions making it challenging for everyday clinical use.

Recently, Physics-Informed Neuronal Networks (PINNs) have shown great potential in the estimation of velocity and pressure in hemodynamics problems. Even though for forward simulations, the existing CFD algorithms perform better than PINNs, for problems where the physics is unknown and partial measurements are available, (namely inverse problems), PINNs have shown outperformed any existing method so far [cites].

2. Objectives of this project

The main goals of this project are:

- The implementation of a PINN, trained on the full NS equations, capable of predict a full high resolution 3D blood velocity field on the aorta, from low resolution 2D PC-MRI images.

- Extract from the resulted field the next physical parameters: a) the Windkessel loads on the aorta outlets, b) the wall shear-stress field and c) the pressure field. Also perform a validation against a classical sequential inverse problem approach.

- Establish a good enough offline training stage, capable of reach fast reconstruction times.

- Explore the clinical applicability of the PINNs on surgical decisions on the cardiovascular system

3. Methodology

Gao et al. presented a decoupled architecture capable of avoid the use of high resolution data for the training stage, leading to the state variables being trained by NS equations. They used the trained PINN in order to increase the resolution of low quality measurements. This approach have shown good results even in the case where the physics was ill-posed or partially known. However, this work was only based on 2D flows with relatively simple geometries and using the stationary form of the NS equations.

In this project we will use 3D time dependent NS equations on realistic aortic geometries.

Synthetic velocity data will be generated using CFD simulations on realistic aortic geometries. We first simulate the blood flow through the aorta as the solution of the incompressible NS equations, coupled with three-element Windkessel boundary conditions at every outlet.

4. Work plan

The total duration of the project is intended in 3 years. A full description of the work plan follows:

First year:

- Implementation of the PINN:  The architecture of the PINN is construct. Different types of learning are tested. The PINN is used in oversimplified scenarios (for the physics and the geometries) in order to test its capabilities of predicting simple parameters. Different types of flow equations and numerical algorithms are tested (monolithic and fractional steps for the Navier-Stokes equations) for the learning stage. Expected duration: 6 months

- Numerical Experiments: Synthetic MRI data will be generated using standard Computational Fluid Dynamics simulations (CFD) on realistic aortic geometries. Coupling with 0D-models will be also present. PINN predictions and training stages are performed with this data. This performance is validated against a Kalman filter approach under the same scenario. A scientific manuscript with this results is prepared. Expected duration: 6 months.

Second year:

- Pressure fields reconstructions: Pressure fields reconstruction using the PINN methodology is tested. Validation against standard methods such as: Bernoulli’s formula, PPE, STE, WARP is done. If results are positive, possible clinical application is explored. Expected time: 4-5 months.

- 2D PC-MRI experiments: Several PC-MRI images are obtained for healthy volunteers at the Center of Biomedical Images (CIB) of the Catholic University. Being the PINN trained on the more sophisticated synthetic data, predictions on the targeted parameters are performed. New experiments only using Navier-Stokes equations and its best discrete approach are performed. Expected time: 4-6 months

Third year:

- 3D PC-MRI experiments: The same than before is done with 4D Flow MRI images. This acquisition can be included on the same protocol than before. The 3D field is set into the PINN formalism for testing: super-resolved resolution (enhance the resolution of the 4D Flow at the simulation level) and parameter extraction separately (Windkessel parameters and wall shear-stress field). Expected time: 7 months

- Clinical Application: The PINN formalism is used on real scenarios for fast parameter extraction from MRI images. Other than aortic flows are explored such as: otros flujos?.  A second manuscript with the real MRI data results is prepared. Expected time: 5-6 months.

4. Work Plan

| Activity | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Literature review | X |  |  |  |  |  |  |  |  |  |  |  |
| Implementation of the PINN | X | X |  |  |  |  |  |  |  |  |  |  |
| Synthetic data experiments |  |  |  |  |  |  |  |  |  |  |  |  |
| - Simulated data generation |  |  | X |  |  |  |  |  |  |  |  |  |
| - Validation againts classic method |  |  | X |  |  |  |  |  |  |  |  |  |
| Real data experiments |  |  |  |  |  |  |  |  |  |  |  |  |
| - PC-MRI acquisitions |  |  |  |  |  | X |  |  |  |  |  |  |
| PINN Super-Resolved resolutions experiments |  |  | X | X |  | X | X | X |  |  |  |  |
| PINN parameter reconstructions |  |  | X | X |  |  | X | X |  |  |  |  |
| Manuscript preparation |  |  |  |  | X |  |  |  | X |  |  |  |

5. Scientific novelty